## Sample Table
Requirement ID | Requirement Description | Test Case ID | Test Type | Priority | Risk Level | Automation Status | Test Execution Status | Linked Defects | Sprint | Reviewer | Last Reviewed On | Notes
REQ-101 | User login with valid credentials | TC-001 | Functional | High | Medium | Automated | Passed |  | Sprint 5 | Pavan | 10.05.2025 | Covered in smoke test
REQ-102 | Show error on invalid login attempt | TC-002 | UI Validation | Medium | Low | Manual | Failed | BUG-0098 | Sprint 5 | Lisa | 10.05.2025 | Error message overlaps with button
REQ-103 | Lock account after 5 failed logins | TC-003 | Security | High | High | Planned | Not run |  | Sprint 6 |  |  | Needs clarification from Product Owner
REQ-104 | Password reset via email | TC-004 | Functional | High | Medium | Manual | Passed |  | Sprint 6 | Eva | 12.05.2025 | Valid token and expiry verified
REQ-105 | Password field must be masked | TC-005 | UI | Low | Low | Automated | Passed |  | Sprint 4 | Tom | 08.05.2025 | Tested on Chrome and Firefox
REQ-106 | Session timeout after 15 minutes | TC-006 | Performance | Medium | High | Manual | Failed | BUG-0101 | Sprint 6 | Pavan | 13.05.2025 | Timeout didn’t trigger on inactivity
REQ-107 | Support multiple languages | TC-007 | Localization | Medium | Medium | Manual | Passed |  | Sprint 6 | Sara | 13.05.2025 | Verified EN, DE, FR texts
REQ-108 | Validate email format in registration | TC-008 | Validation | High | Medium | Automated | Passed |  | Sprint 5 | Max | 09.05.2025 | Regex validation for multiple formats
REQ-109 | Mobile responsiveness of login page | TC-009 | UI/Responsive | Medium | Medium | Manual | Passed |  | Sprint 6 | Pavan | 12.05.2025 | Tested on iOS and Android
REQ-110 | Show user-friendly error codes | TC-010 | Error Handling | Low | Low | Planned | Not run |  | Sprint 7 |  |  | Awaiting detailed error spec
REQ-111 | Track login attempts per IP | TC-011 | Security | High | High | Manual | Passed |  | Sprint 6 | Eva | 13.05.2025 | Tested with simulated IP range

## Sheet2
Recommended columns for the Requirements Traceability Matrix table
Column | Description
Requirement ID | Unique ID from the requirements specification / Jira / specification
Requirement Description | Brief description of the requirement
Test Case ID(s) | Linked test case IDs (e.g. TC_Login_001)
Test Case Description | Goal of the test case in 1 sentence
Test Type | E.g. “Functional”, “UI”, “Security”, “Performance”
Priority / Risk Level | High / Medium / Low (from risk assessment or MoSCoW)
Automation Status | Manual / Automated / Planned
Test Execution Status | Scheduled / Passed / Failed / Blocked
Linked Defects (Bug ID) | If errors were found, enter bug IDs
Last Reviewed On | Date of last update of requirement or tests
Reviewer / Tester | Responsible person